## Appendix_A_SSP_Gap_Matrix
Control ID | CMMC Practice | Practice Statement | Current Score | Max Score | Compliance % | Risk Level | Gap Description | Remediation Action | Estimated Cost | Timeline (Days) | Owner
3.5.3 | IA.L2-3.5.3 | Multifactor Authentication for privileged and non-privileged accounts | 0 | 5 | 0% | CRITICAL | MFA has not been implemented and configured on all applicable applications and devices. No MFA for privileged accounts (network/local access) or non-privileged accounts (network access). | Enable MFA in Entra ID for all users. Deploy hardware tokens for privileged accounts. Configure Conditional Access policies. | $57,000 - $85,500 | 30 | Dana Ellis
3.1.18 | AC.L2-3.1.18 | Control connection of mobile devices | 0 | 5 | 0% | HIGH | Pending implementation of InTune for mobile device management. Mobile devices that process/store/transmit CUI are not identified. No MDM solution deployed. Mobile device connections are not authorized via technical controls. | Deploy Microsoft Intune MDM. Create mobile device inventory. Configure device enrollment policies and compliance rules. Implement Conditional Access to block unmanaged devices. | $85,500 - $114,000 | 60-90 | Dana Ellis
3.1.19 | AC.L2-3.1.19 | Encrypt CUI on mobile devices and mobile computing platforms | 0 | 3 | 0% | HIGH | Laptops have BitLocker enabled but mobile devices (phones/tablets) not enrolled in MDM. Encryption cannot be verified. No centralized enforcement or reporting. | Deploy Intune MDM (addresses 3.1.18 and 3.1.19 together). Configure encryption enforcement policies. Generate encryption compliance reports from Intune. | Included in 3.1.18 | 60-90 | Dana Ellis
3.1.3 | AC.L1-3.1.3 | Control the flow of CUI in accordance with approved authorizations | Partial | 5 | 40% | HIGH | CUI-facing users need to be identified and segmented using Conditional Access through Office 365/SharePoint. Data flow specific to CUI is documented in network diagrams but technical controls incomplete. | Migrate to Microsoft GCC (or GCC High if classified work confirmed). Implement Conditional Access policies. Deploy Azure AD Firewall and VPN with traffic monitoring. | $171,000 - $285,000 (GCC) or $342,000 - $570,000 (GCC High) | 60-90 | Dana Ellis
3.5.6 | IA.L2-3.5.6 | Disable identifiers after defined period of inactivity | Partial | 5 | 60% | MEDIUM | Inconsistent processes for disabling user accounts within required timeframes (24-72 hours post-termination). No automated account lifecycle management. Dormant account identification incomplete. | Implement automated account disablement workflows in Entra ID. Configure account expiration policies tied to HR termination dates. Establish quarterly access reviews for dormant accounts. | $17,100 - $28,500 | 30-45 | Dana Ellis
3.8.1 | MP.L2-3.8.1 | Protect CUI media during transport outside controlled areas | Partial | 3 | 50% | MEDIUM | Media transport procedures exist but lack encryption validation and chain-of-custody documentation. | Establish media transport policy with encryption requirements. Implement logging for media movement. Train personnel on CUI handling during transport. | $11,400 - $17,100 | 30 | Dana Ellis
3.8.3 | MP.L2-3.8.3 | Sanitize or destroy information system media | Partial | 5 | 40% | MEDIUM | Media sanitization procedures incomplete. No documented disposal records. Vendor certification for destruction not consistently obtained. | Implement media sanitization policy compliant with NIST SP 800-88. Establish vendor relationships for certified media destruction. Create disposal logs and audit trail. | $17,100 - $28,500 | 45-60 | Dana Ellis
3.8.9 | MP.L2-3.8.9 | Protect CUI confidentiality when stored on portable storage devices | Partial | 3 | 60% | MEDIUM | Policy exists to restrict portable storage with CUI but technical enforcement (DLP) not deployed. USB device control incomplete. | Deploy endpoint DLP solution to block unauthorized portable media. Implement USB device whitelisting. Create approved portable media registry. | $22,800 - $34,200 | 45-60 | Dana Ellis
3.1.20 | AC.L1-3.1.20 | Verify and control/limit connections to and use of external systems | 1 | 1 | 100%* | MEDIUM | Marked as implemented but SSP notes "needs improvements". External system connections identified but lack formal authorization documentation. | Document and formally authorize all external system connections (partner networks cloud services). Update external connection registry. Review and approve quarterly. | $5,700 - $11,400 | 30 | Dana Ellis
3.4.7 | CM.L2-3.4.7 | Restrict configure and monitor wireless access | Partial | 5 | 60% | MEDIUM | Wireless access points use WPA2 but lack enterprise-grade authentication (802.1X). Network segmentation between CUI and non-CUI incomplete. | Upgrade wireless infrastructure to WPA3-Enterprise with RADIUS authentication. Implement VLANs isolating CUI networks. Deploy next-gen firewall with deep packet inspection. | $171,000 - $285,000 | 90-120 | Dana Ellis
3.1.1 | AC.L1-3.1.1 | Limit information system access to authorized users | 5 | 5 | 100% | LOW | Access Control Policy in place. User access provisioning processes documented and implemented. | Maintain current controls. Annual policy review. | N/A | N/A | Dana Ellis
3.1.2 | AC.L1-3.1.2 | Limit information system access to the types of transactions and functions that authorized users are permitted | 5 | 5 | 100% | LOW | Role-based access control (RBAC) implemented in Active Directory and key applications. Least privilege principles applied. | Maintain current controls. Quarterly access reviews. | N/A | N/A | Dana Ellis
3.1.5 | AC.L1-3.1.5 | Employ the principle of least privilege | 5 | 5 | 100% | LOW | Least privilege documented in Access Control Policy. Admin accounts separated from user accounts. Privileged access limited to authorized personnel. | Maintain current controls. Semi-annual privileged access reviews. | N/A | N/A | Dana Ellis
3.1.12 | AC.L2-3.1.12 | Monitor and control remote access sessions | 4 | 5 | 80% | LOW | VPN access controlled and logged. Remote access limited to authorized users. Minor gap: session timeout policies need tuning. | Adjust VPN session timeout policies. Implement idle session termination (2 hours). | $5,700 | 15 | Dana Ellis
3.1.16 | AC.L2-3.1.16 | Authorize wireless access prior to allowing such connections | 5 | 5 | 100% | LOW | All access points set to WPA2 encryption with complex passcodes. Wireless access authorization process documented. | Maintain current controls. Migrate to WPA3 as part of 3.4.7 remediation. | N/A | N/A | Dana Ellis
3.1.17 | AC.L2-3.1.17 | Protect wireless access using authentication and encryption | 5 | 5 | 100% | LOW | Wireless access protected via WPA2 with authentication and encryption. SIEM monitoring in place for wireless connections. | Maintain current controls. Upgrade to WPA3-Enterprise with 3.4.7 remediation. | N/A | N/A | Dana Ellis
3.1.21 | AC.L2-3.1.21 | Limit use of portable storage devices on external systems | 1 | 1 | 100% | LOW | Policy in place to restrict portable storage with CUI unless approved and documented. Technical controls to be enhanced with DLP (see 3.8.9). | Maintain policy. Deploy DLP technical controls per 3.8.9. | Included in 3.8.9 | N/A | Dana Ellis
3.3.1 | AU.L2-3.3.1 | Create and retain system audit logs and records | 5 | 5 | 100% | LOW | Audit logging enabled across systems. SIEM (ConnectWise) deployed for log aggregation. 90-day retention configured. | Maintain current controls. Extend retention to 1 year as budget allows. | N/A | N/A | Dana Ellis
3.3.2 | AU.L2-3.3.2 | Ensure that actions of individual system users can be traced | 5 | 5 | 100% | LOW | User activity logging enabled. Individual user actions traceable through audit logs and SIEM correlation. | Maintain current controls. | N/A | N/A | Dana Ellis
3.4.1 | CM.L2-3.4.1 | Establish and maintain baseline configurations | 4 | 5 | 80% | LOW | Baseline configurations documented for servers and workstations. Minor gap: mobile device baselines pending Intune deployment. | Complete mobile device baseline configuration with Intune deployment (see 3.1.18). | Included in 3.1.18 | N/A | Dana Ellis
3.4.2 | CM.L2-3.4.2 | Employ change control for system changes | 5 | 5 | 100% | LOW | Change control process documented and followed. Change Advisory Board (CAB) reviews major changes. Change tickets tracked in ticketing system. | Maintain current controls. | N/A | N/A | Dana Ellis
3.5.1 | IA.L1-3.5.1 | Identify information system users | 5 | 5 | 100% | LOW | User identification via unique usernames in Active Directory. No shared accounts for CUI access. | Maintain current controls. | N/A | N/A | Dana Ellis
3.5.2 | IA.L1-3.5.2 | Authenticate organizational users | 4 | 5 | 80% | MEDIUM | Password authentication implemented. Passwords meet complexity requirements. Gap: MFA not deployed (see 3.5.3). | Deploy MFA per 3.5.3 remediation. | Included in 3.5.3 | N/A | Dana Ellis
3.5.7 | IA.L2-3.5.7 | Enforce a minimum password complexity | 5 | 5 | 100% | LOW | Password complexity policy enforced via Active Directory Group Policy. Minimum 14 characters required with complexity requirements. | Maintain current controls. | N/A | N/A | Dana Ellis
3.5.8 | IA.L2-3.5.8 | Prohibit password reuse | 5 | 5 | 100% | LOW | Password history policy enforced (24 previous passwords). Password reuse prohibited. | Maintain current controls. | N/A | N/A | Dana Ellis
3.5.9 | IA.L2-3.5.9 | Allow temporary password use for system logons with immediate change | 5 | 5 | 100% | LOW | Temporary passwords expire on first use. Users forced to change password on initial login. | Maintain current controls. | N/A | N/A | Dana Ellis
3.6.1 | IR.L2-3.6.1 | Establish operational incident-handling capability | 4 | 5 | 80% | LOW | Incident response plan documented. Incident response team identified. Minor gap: annual IR tabletop exercise not yet conducted. | Conduct annual IR tabletop exercise. Update IR plan based on lessons learned. | $11,400 | 60 | Dana Ellis
3.6.2 | IR.L2-3.6.2 | Track document and report incidents | 5 | 5 | 100% | LOW | Incidents tracked in ticketing system. Reporting procedures documented. DoD 72-hour breach notification requirement documented. | Maintain current controls. | N/A | N/A | Dana Ellis
3.7.1 | MA.L2-3.7.1 | Perform maintenance on organizational information systems | 5 | 5 | 100% | LOW | Maintenance procedures documented. Scheduled maintenance windows established. Maintenance activities logged. | Maintain current controls. | N/A | N/A | Dana Ellis
3.7.2 | MA.L2-3.7.2 | Provide controls on tools techniques and personnel for maintenance | 5 | 5 | 100% | LOW | Maintenance tool access restricted to authorized personnel. Vendor maintenance access controlled and monitored. | Maintain current controls. | N/A | N/A | Dana Ellis
3.11.1 | RA.L2-3.11.1 | Periodically assess the risk to organizational operations | 4 | 5 | 80% | LOW | Annual risk assessment conducted. Risk register maintained. Minor gap: risk assessment frequency should increase to semi-annual. | Increase risk assessment frequency to semi-annual. Update risk register quarterly. | $5,700 | 30 | Dana Ellis
3.12.1 | SA.L2-3.12.1 | Periodically assess security controls | 3 | 5 | 60% | MEDIUM | Security control assessments performed but not on consistent schedule. Gap: Need to establish annual assessment cycle with C3PAO. | Establish annual security control assessment with independent C3PAO. Budget for annual reassessment every 3 years. | $34,200 - $57,000 (every 3 years) | N/A | Dana Ellis
3.13.1 | SC.L1-3.13.1 | Monitor control and protect communications at external boundaries | 4 | 5 | 80% | MEDIUM | Firewall deployed at network boundary. SIEM monitoring in place. Gap: Firewall needs upgrade for deep packet inspection and intrusion prevention (see 3.4.7). | Upgrade to next-gen firewall per 3.4.7 remediation. | Included in 3.4.7 | N/A | Dana Ellis
3.13.5 | SC.L2-3.13.5 | Implement cryptographic mechanisms to prevent unauthorized disclosure during transmission | 5 | 5 | 100% | LOW | TLS/SSL encryption enforced for data in transit. VPN encryption for remote access. Email encryption (Office 365) deployed. | Maintain current controls. | N/A | N/A | Dana Ellis
3.14.1 | SI.L1-3.14.1 | Identify report and correct system flaws in a timely manner | 5 | 5 | 100% | LOW | Patch management process documented. Patches deployed within 30 days of release (critical within 7 days). Vulnerability scanning performed monthly. | Maintain current controls. | N/A | N/A | Dana Ellis
3.14.2 | SI.L1-3.14.2 | Provide protection from malicious code | 5 | 5 | 100% | LOW | Microsoft Defender deployed across endpoints. Real-time malware protection enabled. Definitions updated daily. | Maintain current controls. | N/A | N/A | Dana Ellis
3.14.4 | SI.L2-3.14.4 | Update malicious code protection mechanisms | 5 | 5 | 100% | LOW | Antivirus definitions updated automatically. Threat intelligence feeds integrated with Defender. | Maintain current controls. | N/A | N/A | Dana Ellis
3.14.6 | SI.L2-3.14.6 | Monitor organizational systems including inbound/outbound communications | 4 | 5 | 80% | MEDIUM | SIEM deployed for monitoring. Network traffic monitoring in place. Gap: Enhanced monitoring capabilities needed with next-gen firewall (see 3.4.7). | Deploy enhanced monitoring with next-gen firewall and MSSP. | Included in 3.4.7 + $85,500 - $114000MSSP (Year 1) | N/A | Dana Ellis
TOTAL ESTIMATED REMEDIATION COST (per Appendix C cost model; per-control figures are indicative) | [9 empty] | $741,000 - $1,140,000