## Appendix_C_Cost_Model
CMMC Level 2 Compliance Cost Model - Meridian Federal Systems Inc.
Prepared by: Chris McConnell Eagle Ridge Advisory
Date: October 1 2025
PHASE 1: INITIAL REMEDIATION (MONTHS 1-6)
Line Item | Unit Cost | Quantity | Low Estimate | High Estimate | Notes | Timeline | Vendor/Owner
A. MULTIFACTOR AUTHENTICATION (3.5.3)
Entra ID P1 Licensing (MFA + Conditional Access) | $7/user/month | 50 users × 12 months | $4,100 | $4,100 | Required for MFA and Conditional Access policies | 12 months | Microsoft
Hardware Security Keys (YubiKey 5 NFC) | $57/key | 10 admin users | $570 | $570 | Privileged account phishing-resistant MFA | Immediate | Yubico
MFA Deployment Services (consultant) | $170/hour | 200-300 hours | $34,200 | $51,300 | Entra ID config Conditional Access setup user enrollment | 30 days | Vantage Point Consulting
MFA User Training (5 sessions) | $2,300/session | 5 sessions | $11,400 | $11,400 | Train users on authenticator apps and MFA procedures | 15 days | Internal/ISI
Authenticator App Licenses (optional Microsoft Authenticator free; Duo backup) | $3/user/month | 50 users × 12 months | $2,050 | $4,100 | Backup to hardware keys for standard users | 12 months | Microsoft/Duo
Contingency Buffer (10%) |  |  |  | $5,150 | $7,200 |  |  | MFA Subtotal:,,,$57 | 470" | $78,670
B. MICROSOFT GCC HIGH MIGRATION (3.1.3 3.1.18 3.1.19)
GCC High Licensing (Office 365 E3) | $40/user/month | 50 users × 12 months | $23,940 | $23,940 | Replaces Commercial O365; 2.3x cost multiplier | 12 months | Microsoft
GCC High Licensing (Intune MDM) | $9/user/month | 50 users × 12 months | $5,450 | $5,450 | Mobile device management licensing | 12 months | Microsoft
GCC High Tenant Setup & Migration Services | $114,000 flat | 1 tenant | $114,000 | $171,000 | Tenant provisioning data migration user cutover | 60-90 days | Microsoft Partner
Data Migration (SharePoint OneDrive Email) | $57/user | 50 users | $2,850 | $5,700 | Per-user migration complexity varies by data volume | 45 days | Migration Partner
User Re-provisioning & Training | $2,300/session | 10 sessions | $22,800 | $34,200 | GCC High environment familiarization | 30 days | Internal/ISI
Network Connectivity (ExpressRoute Direct setup optional) | $5,700 - $11,400 | 1 circuit | $5,700 | $11,400 | Dedicated circuit for classified work if required | 30 days | Network Provider
Eligibility Validation & Authorization (DISA) | $5 | 700 flat | 1 engagement | $5,700 | $5,700 | Validate GCC High eligibility with DISA/DoD | 15 days | DISA
Testing & Validation (UAT) | $11,400 | 1 phase | $11,400 | $17,100 | User acceptance testing post-migration | 21 days | Vantage Point Consulting
GCC High cutover downtime (productivity loss estimate) | $570/user | 50 users | $28,500 | $57,000 | Estimated 1-2 days productivity loss during cutover | 2-3 days | N/A
Contingency Buffer (15%) |  |  |  | $33,396 | $49,043 |  |  | GCC High Migration Subtotal:,,,$253 | 736" | $374,833
ALTERNATE: If GCC (not High) is sufficient:
GCC Licensing (Office 365 E3) | $21/user/month | 50 users × 12 months | $12,312 | $12,312 | Lower cost if no classified work | 12 months | Microsoft
GCC Migration Services (simpler than High) | $57 | 000 flat | 1 tenant | $57,000 | $85,500 | Less complex than GCC High | 45-60 days | Microsoft Partner
GCC Alternate Subtotal: |  |  | $69,312 | $97,812
C. INTUNE MDM DEPLOYMENT (3.1.18 3.1.19)
Intune Licensing | (Included in GCC High licensing above) |  | $0 | $0 |  |  | Mobile Device Inventory & Discovery,$115/device,40 devices,$4 | 550" | $6,850 | Identify all mobile devices accessing CUI | 15 days | Internal IT
Device Enrollment Services (Intune config) | $170/hour | 150-250 hours | $25,650 | $42,750 | Configure policies enrollment workflows compliance rules | 45 days | Vantage Point Consulting
Mobile App Management (MAM) Configuration | $170/hour | 50-100 hours | $8,550 | $17,100 | Configure app protection policies for O365 mobile apps | 30 days | Vantage Point Consulting
Conditional Access Policies (Intune integration) | $170/hour | 40-80 hours | $6,850 | $13,680 | Block unmanaged devices require compliant devices | 21 days | Vantage Point Consulting
BitLocker Validation (laptops) | $57/device | 30 laptops | $1,700 | $2,850 | Validate and enforce encryption on all Windows devices | 14 days | Internal IT
iOS/Android Native Encryption Enforcement | $57/device | 20 mobile devices | $1,150 | $2,300 | Enforce device encryption on smartphones and tablets | 14 days | Internal IT
User Training (MDM enrollment mobile security) | $2,300/session | 3 sessions | $6,850 | $9,100 | Train users on device enrollment and mobile security | 15 days | Internal/ISI
Testing & Rollout (pilot + full deployment) | $11 | 400 flat | 1 phase | $11,400 | $17,100 | Pilot with 10 users then full rollout | 30 days | Vantage Point Consulting
Contingency Buffer (10%) |  |  |  | $6,650 | $11,172 |  |  | Intune MDM Subtotal:,,,$73 | 350" | $122,902
D. FIREWALL & NETWORK SEGMENTATION (3.4.7 3.1.20)
Next-Gen Firewall (Palo Alto PA-440 or similar) | $17,100 - $28,500 | 2 units (primary + backup) | $34,200 | $57,000 | Deep packet inspection IPS TLS decryption | 90 days | Palo Alto/Fortinet
Firewall Licensing (3-year subscription) | $5,700/year | 3 years × 2 units | $34,200 | $45,600 | Threat prevention URL filtering WildFire | 36 months | Palo Alto/Fortinet
Network Design & Segmentation Services | $230/hour | 100-200 hours | $22,800 | $45,600 | Design VLANs segment CUI network firewall rules | 60 days | Network Consultant
Wireless Infrastructure Upgrade (WPA3-Enterprise) | $1,150/AP | 6-10 access points | $6,850 | $11,400 | Replace or upgrade APs for 802.1X and WPA3 | 45 days | Cisco/Aruba
RADIUS Server Setup (for 802.1X authentication) | $5 | 700 flat | 1 server | $5,700 | $9,100 | Centralized wireless authentication via Entra ID | 30 days | Network Consultant
Network Switch Upgrades (VLAN support) | $2,300/switch | 3-5 switches | $6,850 | $11,400 | Upgrade switches for VLAN tagging and segmentation | 30 days | Cisco/HP
Installation & Configuration Services | $230/hour | 150-250 hours | $34,200 | $57,000 | Physical installation cabling config testing | 60 days | Network Integrator
Penetration Test (post-deployment) | $17 | 100 flat | 1 test | $17,100 | $22,800 | Validate network segmentation and firewall rules | 14 days | CyberSec Firm
Contingency Buffer (15%) |  |  |  | $24,282 | $38,988 |  |  | Firewall & Network Subtotal:,,,$186 | 182" | $298,888
E. SIEM & LOG MONITORING (3.14.6 3.3.1)
SIEM Platform Licensing (Splunk QRadar or MSSP) | $22,800 - $34,200 | 1 platform | $22,800 | $34,200 | Log ingestion storage alerting | 12 months | Splunk/MSSP
SIEM Deployment Services | $230/hour | 80-120 hours | $18,240 | $27,360 | Install configure log sources create dashboards | 45 days | MSSP/Consultant
Log Source Integration (15-20 sources) | $570/source | 15-20 sources | $8,550 | $11,400 | Connect firewalls servers endpoints AD to SIEM | 30 days | MSSP
Threat Intelligence Feed Integration | $5 | 700 flat | 1 feed | $5,700 | $9,100 | Integrate threat intel for correlation and alerting | 14 days | MSSP
Alerting & Use Case Development | $230/hour | 40-60 hours | $9,100 | $13,680 | Create custom alerts for CMMC-relevant events | 30 days | MSSP
90-Day Retention Storage Expansion | $2,300 - $5,700 | 1 expansion | $2,300 | $5,700 | Expand storage for 90-day log retention requirement | 14 days | MSSP/Splunk
Contingency Buffer (10%) |  |  |  | $6,650 | $10,146 |  |  | SIEM Subtotal:,,,$73 | 340" | $111,586
F. CONSULTING & PROGRAM MANAGEMENT
CMMC Consultant (Vantage Point Consulting continuation) | $170/hour | 200-400 hours | $34,200 | $68,400 | Remediation oversight SSP updates coordination | 180 days | Vantage Point Consulting
C3PAO Pre-Assessment (gap validation) | $11 | 400 flat | 1 assessment | $11,400 | $17,100 | Independent validation of remediation completeness | 14 days | Independent C3PAO
Project Manager (internal or external) | $115/hour | 200 hours | $22,800 | $34,200 | Coordinate vendors manage timeline report to Bayline | 180 days | Internal/External
Documentation Updates (SSP POA&M policies) | $170/hour | 60-100 hours | $10,260 | $17,100 | Update SSP close POA&Ms revise policies | 90 days | Vantage Point Consulting
Contingency Buffer (10%) |  |  |  | $7,850 | $13,680 |  |  | Consulting Subtotal:,,,$86 | 510" | $150,480
G. MISCELLANEOUS & CONTINGENCIES
Security Awareness Training (all employees) | $57/user | 50 users | $2,850 | $3,400 | Annual security training CMMC-focused | Ongoing | KnowBe4/ISI
Vulnerability Scanning Tool (Nessus Qualys) | $3,400 - $5,700 | 1 license | $3,400 | $5,700 | Monthly vulnerability scans for compliance | 12 months | Tenable/Qualys
Asset Inventory Tool (if not in Intune) | $2,300 - $5,700 | 1 license | $2,300 | $5,700 | Hardware/software asset tracking | 12 months | SnipeIT/Intune
Miscellaneous Subtotal: |  |  | $8,550 | $14,800
PHASE 1 TOTAL (MONTHS 1-6): |  |  | $739,138 | $1,152,159
ROUNDED PHASE 1 TOTAL: |  |  | $741,000 | $1,140,000
RECOMMENDATION: Budget $941K (midpoint of $741K-$1 | 140K; GCC High migration included)
PHASE 2: YEAR 1 OPERATING EXPENSES (MONTHS 7-12)
Line Item | Monthly Cost | Months | Low Estimate | High Estimate | Notes | Vendor/Owner
A. MANAGED SECURITY SERVICES (MSSP)
24/7 SOC Monitoring | $5 | 700/month | 6 months | $34,200 | $45,600 | SIEM monitoring alert triage incident response retainer | MSSP
SIEM Platform Licensing (ongoing) | $2 | 850/month | 6 months | $17,100 | $22,800 | Splunk/QRadar licensing post-initial | MSSP/Splunk
Threat Intelligence Feeds | $570/month | 6 months | $3,400 | $4,550 | Ongoing threat intel updates | MSSP
MSSP Subtotal (6 months): |  |  | $54,700 | $72,950
B. MICROSOFT GCC HIGH LICENSING (ONGOING)
GCC High Office 365 E3 | $40/user/month | 50 users × 6 months | $11,970 | $11,970 | Ongoing post-migration | Microsoft
GCC High Intune MDM | $9/user/month | 50 users × 6 months | $2,750 | $2,750 | Ongoing MDM licensing | Microsoft
GCC High ExpressRoute (if required) | $1 | 150/month | 6 months | $6,850 | $6,850 | Dedicated circuit monthly cost | Microsoft Azure
GCC High Subtotal (6 months): |  |  | $21,570 | $21,570
C. CONSULTING & COMPLIANCE MAINTENANCE
C3PAO Formal Assessment | $39 | 900 flat | 1 assessment | $39,900 | $57,000 | Official CMMC Level 2 certification assessment (Month 9-10) | Independent C3PAO
CMMC Consultant (ongoing support) | $11 | 400/month | 3 months | $34,200 | $45,600 | Post-remediation support audit prep | Vantage Point Consulting
Annual SSP Update & Maintenance | $5 | 700 flat | 1 update | $5,700 | $9,100 | Annual SSP refresh | Vantage Point Consulting
POA&M Closeout Documentation | $3 | 400 flat | 1 closeout | $3,400 | $5,700 | Final POA&M closure evidence collection | Vantage Point Consulting
Consulting Subtotal (6 months): |  |  | $83,200 | $117,400
D. ONGOING OPERATIONAL COSTS
Vulnerability Scanning (continued) | $570/month | 6 months | $3,400 | $5,700 | Monthly scans | Tenable/Qualys
Security Awareness Training (refresher) | $2 | 300 flat | 1 training | $2,300 | $3,400 | Mid-year refresher training | KnowBe4
Firewall Maintenance & Updates | $1 | 150/month | 6 months | $6,850 | $9,100 | Firewall signature updates | Palo Alto
Operational Subtotal (6 months): |  |  | $12,550 | $18,200
E. INTERNAL STAFFING (INCREMENTAL)
Cybersecurity Analyst (fractional FTE) | $34,200 - $45,600 | 6 months (0.5 FTE) | $17,100 | $22,800 | Internal hire or contractor to support compliance | Internal
IT Director Bonus (retention) | $11 | 400 flat | 1 bonus | $11,400 | $11,400 | Dana Ellis retention through certification | Internal
Staffing Subtotal (6 months): |  |  | $28,500 | $34,200
YEAR 1 OPEX TOTAL (MONTHS 7-12): |  |  | $200,520 | $264,320
ROUNDED YEAR 1 OPEX TOTAL: |  |  | $205,200 | $262,200
PHASE 3: YEARS 2-5 RECURRING OPERATING EXPENSES
Assumed Revenue Base: | $22.8M - $34.2M annually | [5 empty] | Compliance OpEx as % of Revenue:,1.5% - 2.5%,,,,,,
Line Item | Annual Cost (Year 2-5) | Years | 4-Year Total Low | 4-Year Total High | Notes | Vendor/Owner
A. MANAGED SECURITY SERVICES (MSSP)
24/7 SOC Monitoring | $91,200 - $136,800 | 4 years | $364,800 | $547,200 | Full year of monitoring | MSSP
SIEM Licensing & Maintenance | $28,500 - $39,900 | 4 years | $114,000 | $159,600 | Annual SIEM platform costs | MSSP/Splunk
Threat Intelligence Feeds | $6,850 - $11,400 | 4 years | $27,360 | $45,600 | Ongoing threat intel | MSSP
MSSP Subtotal (Years 2-5): |  |  |  | $506,160 | $752,400
B. MICROSOFT GCC HIGH LICENSING
GCC High Office 365 E3 | $23,940/year | 4 years | $95,760 | $95,760 | 50 users @ $40/month | Microsoft
GCC High Intune MDM | $5,450/year | 4 years | $21,888 | $21,888 | 50 users @ $9/month | Microsoft
GCC High ExpressRoute (if required) | $13,680/year | 4 years | $54,720 | $54,720 | Dedicated circuit | Microsoft Azure
User Growth (10% annually) | 10% increase | Compounded | $17,442 | $17,442 | Assume 5 users added per year | Microsoft
GCC High Subtotal (Years 2-5): |  |  |  | $189,810 | $189,810
C. COMPLIANCE & AUDIT
C3PAO Reassessment (every 3 years) | $39,900 - $57,000 | 1 assessment (amortized) | $53,200 | $76,000 | Required every 3 years (Year 4) amortized over 4 years | Independent C3PAO
Annual SSP Update | $5,700 - $9,100 | 4 years | $22,800 | $36,480 | Annual documentation refresh | Vantage Point Consulting
Annual Security Control Testing (internal) | $11,400 - $17,100 | 4 years | $45,600 | $68,400 | Annual internal testing | Internal/Consultant
Compliance Subtotal (Years 2-5): |  |  |  | $121,600 | $180,880
D. ONGOING OPERATIONAL TOOLS
Vulnerability Scanning | $6,850 - $11,400 | 4 years | $27,360 | $45,600 | Annual vulnerability scanning | Tenable/Qualys
Security Awareness Training | $2,850 - $3,400 | 4 years | $11,400 | $13,680 | Annual employee training | KnowBe4
Firewall Maintenance & Upgrades | $13,680 - $22,800 | 4 years | $54,720 | $91,200 | Annual firewall updates hardware refresh (Year 5) | Palo Alto
DLP Tool (Data Loss Prevention) | $11,400 - $17,100 | 4 years | $45,600 | $68,400 | USB control portable media protection | Symantec/McAfee
Operational Tools Subtotal (Years 2-5): |  |  |  | $139,080 | $218,880
E. INTERNAL STAFFING
Cybersecurity Analyst (1 FTE) | $91,200 - $114,000 | 4 years | $364,800 | $456,000 | Full-time cybersecurity analyst hire | Internal
IT Director Compensation Increase | $11,400 - $17,100 | 4 years | $45,600 | $68,400 | Market adjustment for CMMC responsibilities | Internal
Staffing Subtotal (Years 2-5): |  |  |  | $410,400 | $524,400
F. INSURANCE & RISK MITIGATION
Cyber Liability Insurance | $17,100 - $28,500 | 4 years | $68,400 | $114,000 | Cyber breach coverage with CMMC endorsement | Insurance Broker
Professional Liability (E&O) Increase | $5,700 - $11,400 | 4 years | $22,800 | $45,600 | Increased coverage for GovCon cyber risk | Insurance Broker
Insurance Subtotal (Years 2-5): |  |  |  | $91,200 | $159,600
YEARS 2-5 TOTAL (4-YEAR AGGREGATE): |  |  |  | $1,458,250 | $2,025,970
ANNUAL AVERAGE (YEARS 2-5): |  |  |  | $364,563 | $506,493
ROUNDED ANNUAL AVERAGE: |  |  |  | $364,800 | $513,000
CUMULATIVE 5-YEAR COST SUMMARY
Phase | Timeframe | Low Estimate | High Estimate | Midpoint | Notes
Initial Remediation | Months 1-6 | $741,000 | $1,140,000 | $940,500 | One-time CapEx
Year 1 Operating Expenses | Months 7-12 | $205,200 | $262,200 | $233,700 | Elevated first-year costs
Year 2 Operating Expenses | Year 2 | $364,800 | $513,000 | $438,900 | Normalized recurring costs
Year 3 Operating Expenses | Year 3 | $364,800 | $513,000 | $438,900 | Normalized recurring costs
Year 4 Operating Expenses | Year 4 | $364,800 | $513,000 | $438,900 | Includes C3PAO reassessment
Year 5 Operating Expenses | Year 5 | $364,800 | $513,000 | $438,900 | Normalized recurring costs
5-YEAR TOTAL: |  | $2,405,400 | $3,454,200 | $2,929,800
ROUNDED 5-YEAR TOTAL: |  | $2,394,000 | $3,420,000 | $2,964,000
NOTE: |  |  |  |  | GCC High migration and licensing are already included in the totals above
SENSITIVITY ANALYSIS
Variable | Base Assumption | Downside Scenario | Upside Scenario | Impact on 5-Year Cost
GCC High vs GCC | GCC High budgeted (~$470K-$590K over 5 years) | GCC sufficient (-$330K to -$430K) | GCC High + ExpressRoute (+$228K) | -$430K to +$228K
MSSP Cost | Full MSSP @ $114K/year | Internal SOC build (-$342K over 5 years) | Enhanced MSSP with IR retainer (+$228K over 5 years) | -$342K to +$228K
User Growth | 10% annually (5 users/year) | No growth (-$57K over 5 years) | 20% growth (+$114K over 5 years) | -$57K to +$114K
C3PAO Reassessment Frequency | Every 3 years | Annual reassessments (+$114K over 5 years) | One-time only (-$57K over 5 years) | -$57K to +$114K
Rework/Gaps Found | 10% contingency buffer | No rework needed (-$85K) | 20% rework required (+$171K) | -$85K to +$171K
BEST CASE (GCC only internal SOC no rework): |  | $1,824,000
BASE CASE (GCC High full MSSP 10% contingency): |  | $2,964,000
WORST CASE (GCC High + rework + annual reassessment): |  | $5,130,000
RECOMMENDATION: Budget $2.4M - $3.4M over 5 years with midpoint at $2.9M