## Appendix_D_POAM_Tracker
POA&M ID | Unique ID | NIST Control | CMMC Practice | Practice Statement | Practice Gaps | Severity | SPRS Points Lost | Recommendation | External Resources Required | Point of Contact | Planned Milestones | Scheduled Completion | Current Status | Blocker | Days Overdue
MFS-0325-001 | MFS-0325-001 | 3.1.3 | AC.L1-3.1.3 | Control the flow of CUI in accordance with approved authorizations | Client needs all CUI facing users identified and segmented using Conditional Access through the Office 365/SharePoint instance. All data flow specific to CUI content is identified within the network diagrams data flow section. | HIGH | -5 | Recommend Migration to Microsoft GCC to utilize conditional access through Office 365/SharePoint instance. The Azure AD Firewall and VPN are configured to monitor and protect traffic. | GCC Migration | Vantage Point Consulting | 1. Validation of client for GCC\n2. Completion of Infrastructure\n3. Migration of Data\n4. Deployment of Firewall/VPN\n5. Go-Live | TBD | Not Started | Requires GCC/GCC High eligibility validation and budget approval | Unknown
MFS-0325-002 | MFS-0325-002 | 3.1.18 | AC.L2-3.1.18 | Control connection of mobile devices | Client needs to put policy is in place dictating that no CUI be stored on mobile devices and conditional access is configured to further limit mobile access. | HIGH | -5 | Policy is in place dictating that no CUI be stored on mobile devices and conditional access is configured to further limit mobile access by using the tool Intune. | GCC Migration | Vantage Point Consulting | 1. Obtain Intune Validation\n2. Install Intune onto all devices\n3. Set up MDM Policy\n4. Go Live | TBD | Not Started | Requires GCC migration completion (dependent on MFS-0325-001) | Unknown
MFS-0325-003 | MFS-0325-003 | 3.1.19 | AC.L2-3.1.19 | Encrypt CUI on mobile devices and mobile computing platforms | Client needs all mobile devices that access CUI encrypted and identified and maintained. | HIGH | -3 | All mobile devices used by CUI facing users must be identified in the network design diagram and approved in the inventory asset list. All mobile devices need to be encrypted with Intune installed to properly manage the devices and CUI data. | GCC Migration | Vantage Point Consulting | 1. Obtain Intune Validation\n2. Install Intune onto all devices\n3. Set up MDM Policy\n4. Go Live | TBD | Not Started | Requires GCC migration and Intune deployment (dependent on MFS-0325-002) | Unknown
MFS-0325-004 | MFS-0325-004 | 3.4.7 | CM.L2-3.4.7 | Restrict configure and monitor wireless access | Wireless infrastructure requires hardening to support WPA3-Enterprise with 802.1X authentication. Current WPA2 configuration insufficient for full CMMC compliance. | MEDIUM | -3 | Upgrade wireless access points to support WPA3-Enterprise. Deploy RADIUS server for 802.1X authentication. Implement network segmentation with VLANs. Deploy next-gen firewall. | Firewall Upgrade / Wireless Infrastructure Upgrade | Vantage Point Consulting + Network Integrator | 1. Firewall procurement and delivery\n2. Wireless AP upgrade\n3. RADIUS server deployment\n4. Network segmentation implementation\n5. Go Live | TBD | In Progress | Requires firewall hardware delivery (45-60 day lead time) | 30 (estimated)
MFS-0325-005 | MFS-0325-005 | 3.5.6 | IA.L2-3.5.6 | Disable identifiers after defined period of inactivity | No automated workflow to disable user accounts within required timeframes (24-72 hours post-termination). Dormant account identification manual and inconsistent. | MEDIUM | -3 | Implement automated account disablement workflows in Entra ID. Configure account expiration policies tied to HR system. Establish quarterly dormant account reviews. | N/A | Dana Ellis | 1. Configure Entra ID automation rules\n2. Integrate with HR system (if available)\n3. Create dormant account review process\n4. Train HR and IT staff | TBD | Not Started | Requires Entra ID configuration (low complexity) | Unknown
MFS-0325-006 | MFS-0325-006 | 3.8.1 | MP.L2-3.8.1 | Protect CUI media during transport outside controlled areas | Media transport procedures exist but lack formal encryption validation and chain-of-custody documentation. No centralized media transport log. | MEDIUM | -1 | Establish formal media transport policy with mandatory encryption requirements. Create chain-of-custody forms and centralized transport log. Train personnel on CUI media handling. | N/A | Dana Ellis | 1. Draft media transport policy\n2. Create transport log template\n3. Procure secure media containers\n4. Conduct training | TBD | Not Started | Low priority (policy-driven control) | Unknown
MFS-0325-007 | MFS-0325-007 | 3.8.3 | MP.L2-3.8.3 | Sanitize or destroy information system media | Media sanitization procedures incomplete. Vendor certification for secure destruction not consistently obtained. Disposal records not maintained. | MEDIUM | -3 | Implement media sanitization policy compliant with NIST SP 800-88 (Clear Purge Destroy methods). Contract with certified destruction vendor (NAID AAA certified). Create disposal audit log. | Certified Media Destruction Vendor | Dana Ellis | 1. Draft media sanitization policy\n2. Select and contract with certified vendor\n3. Create disposal log database\n4. Train IT staff on procedures | TBD | Not Started | Requires vendor procurement | Unknown
MFS-0325-008 | MFS-0325-008 | 3.8.9 | MP.L2-3.8.9 | Protect CUI confidentiality when stored on portable storage devices | Policy restricts portable storage with CUI but no technical enforcement (DLP). USB device control not enabled. Approved portable media not tracked. | MEDIUM | -1 | Deploy endpoint DLP solution to block unauthorized portable media (USB external HDD). Implement USB device whitelisting via Intune. Create approved portable media registry. | DLP Tool (Symantec/McAfee) | Dana Ellis | 1. Procure DLP tool\n2. Configure USB device control policies\n3. Create approved device registry\n4. Deploy and test | TBD | Not Started | Requires DLP tool procurement and Intune deployment | Unknown
MFS-0325-009 | MFS-0325-009 | 3.1.20 | AC.L1-3.1.20 | Verify and control/limit connections to and use of external systems | External connections (partner VPNs cloud services) identified but lack formal authorization documentation. No quarterly review process. | MEDIUM | -1 | Document all external system connections with formal authorization forms. Create external connection registry with business justification and security controls. Establish quarterly review cycle. | N/A | Dana Ellis | 1. Inventory all external connections\n2. Create authorization form template\n3. Obtain management approvals\n4. Establish review schedule | TBD | In Progress | Low complexity (documentation task) | 15 (estimated)
MFS-0325-010 | MFS-0325-010 | 3.5.2 | IA.L1-3.5.2 | Authenticate organizational users | Password authentication implemented with complexity requirements. Gap: MFA not deployed (see POA&M MFS-0325-001 for MFA remediation). | MEDIUM | -1 | Deploy MFA per MFS-0325-001. This POA&M will close automatically when MFA is fully implemented. | Included in MFS-0325-001 | Dana Ellis | Dependent on MFS-0325-001 (MFA deployment) | TBD | Not Started | Dependent on MFS-0325-001 | Unknown
MFS-0325-011 | MFS-0325-011 | 3.6.1 | IR.L2-3.6.1 | Establish operational incident-handling capability | Incident response plan documented and IR team identified. Gap: Annual IR tabletop exercise not yet conducted. IR plan not tested in realistic scenario. | LOW | -1 | Conduct annual IR tabletop exercise simulating CUI breach scenario. Engage external facilitator. Document lessons learned and update IR plan. Establish annual exercise schedule. | IR Tabletop Facilitator (optional) | Dana Ellis | 1. Schedule IR tabletop exercise\n2. Develop breach scenario\n3. Conduct exercise with IR team\n4. Document lessons learned\n5. Update IR plan | TBD | Not Started | Low priority (testing/validation) | Unknown
MFS-0325-012 | MFS-0325-012 | 3.11.1 | RA.L2-3.11.1 | Periodically assess the risk to organizational operations | Annual risk assessment conducted. Risk register maintained. Gap: Risk assessment frequency should increase to semi-annual (every 6 months) per industry best practice. | LOW | -1 | Increase risk assessment frequency to semi-annual. Update risk register quarterly with new threats and vulnerabilities. Brief management on risk posture changes. | N/A | Dana Ellis | 1. Establish semi-annual assessment schedule\n2. Conduct next risk assessment\n3. Update risk register quarterly\n4. Brief management | TBD | Not Started | Low priority (frequency adjustment) | Unknown
MFS-0325-013 | MFS-0325-013 | 3.12.1 | SA.L2-3.12.1 | Periodically assess security controls | Security control assessments performed but not on consistent annual schedule. Gap: Establish annual security control assessment cycle with independent C3PAO. | MEDIUM | -3 | Establish annual security control assessment with independent C3PAO. Budget $34K-$57K for annual assessment. C3PAO certification required every 3 years (assessments in Years 1 3 6 etc.). | Independent C3PAO | Dana Ellis | 1. Select independent C3PAO\n2. Schedule initial CMMC assessment\n3. Establish 3-year reassessment cycle\n4. Budget for annual internal assessments | TBD | Not Started | Requires C3PAO selection (see Section 2.6 in report) | Unknown
MFS-0325-014 | MFS-0325-014 | 3.13.1 | SC.L1-3.13.1 | Monitor control and protect communications at external boundaries | Firewall deployed at network boundary. SIEM monitoring in place. Gap: Firewall lacks deep packet inspection and intrusion prevention capabilities. Requires next-gen firewall upgrade (see MFS-0325-004). | MEDIUM | -1 | Upgrade to next-gen firewall with deep packet inspection IPS/IDS and TLS decryption. Deploy threat prevention subscription. | Included in MFS-0325-004 | Dana Ellis | Dependent on MFS-0325-004 (Firewall upgrade) | TBD | In Progress | Dependent on MFS-0325-004 | 30 (estimated)
MFS-0325-015 | MFS-0325-015 | 3.14.6 | SI.L2-3.14.6 | Monitor organizational systems including inbound/outbound communications | SIEM deployed for monitoring. Network traffic monitoring in place. Gap: Enhanced monitoring capabilities needed with MSSP SOC for 24/7 coverage. Current monitoring is business-hours only. | MEDIUM | -1 | Deploy MSSP for 24/7 SOC monitoring. Enhance SIEM alerting with threat intelligence feeds. Establish SLA for alert triage and incident response. | MSSP / SOC Services | Dana Ellis | 1. Select MSSP vendor\n2. Integrate MSSP with SIEM\n3. Define alerting SLAs\n4. Establish escalation procedures | TBD | Not Started | Requires MSSP vendor procurement | Unknown
MFS-0325-016 | MFS-0325-016 | 3.4.1 | CM.L2-3.4.1 | Establish and maintain baseline configurations | Baseline configurations documented for servers and workstations. Gap: Mobile device baselines pending Intune deployment. No enforcement of baseline compliance. | MEDIUM | -1 | Complete mobile device baseline configuration with Intune deployment (see MFS-0325-002). Enforce baseline compliance via Intune configuration profiles. Generate monthly compliance reports. | Included in MFS-0325-002 | Dana Ellis | Dependent on MFS-0325-002 (Intune deployment) | TBD | Not Started | Dependent on MFS-0325-002 | Unknown
MFS-0325-017 | MFS-0325-017 | 3.3.1 | AU.L2-3.3.1 | Create and retain system audit logs and records | Audit logging enabled. SIEM deployed. 90-day retention configured. Gap: Industry best practice and some DoD contracts require 1-year retention. Storage expansion needed. | LOW | -1 | Extend log retention from 90 days to 1 year. Expand SIEM storage capacity. Estimate $11K-$23K for additional storage. | SIEM Storage Expansion | Dana Ellis | 1. Calculate storage requirements for 1-year retention\n2. Procure additional SIEM storage\n3. Configure retention policies\n4. Test retention and archival | TBD | Not Started | Low priority (best practice not mandatory) | Unknown
MFS-0325-018 | MFS-0325-018 | Various | Various | Annual CMMC certification maintenance | Ongoing requirement to maintain CMMC Level 2 certification through continuous monitoring control effectiveness documentation and periodic reassessment. | ONGOING | N/A | Establish continuous compliance program: quarterly security reviews annual SSP updates POA&M management C3PAO reassessment every 3 years. Budget $34K-$57K annually for compliance maintenance. | Various (MSSP C3PAO Consultants) | Dana Ellis | 1. Establish quarterly compliance review meetings\n2. Assign compliance owner (Dana Ellis)\n3. Budget for annual compliance costs\n4. Schedule Year 3 C3PAO reassessment | Ongoing | Ongoing | N/A | N/A
POA&M SUMMARY STATISTICS
Total POA&M Items: | 18
HIGH Severity: | 3 (MFS-0325-001 002 003) | [6 empty] | Status: All Not Started
MEDIUM Severity: | 11 (MFS-0325-004-010 013-016) | [6 empty] | Status: 3 In Progress 8 Not Started
LOW Severity: | 3 (MFS-0325-011 012 017) | [6 empty] | Status: All Not Started
ONGOING: | 1 (MFS-0325-018) | [6 empty] | Continuous compliance requirement
Total SPRS Points Lost: | -35 points across tracked items (3.5.3/MFA is tracked in the SSP as an immediate priority; not a POA&M milestone) | [6 empty] | Current SPRS Score: 76 (per Vantage Point Consulting SSP assessment)
Target SPRS Score: | 110 (full compliance) | [6 empty] | Gap: 34 points
Minimum Passing Score: | 88 (80% compliance) | [6 empty] | Gap: 12 points to minimum
CRITICAL PATH ANALYSIS
Longest Lead Time Items: | [8 empty] | Estimated Days
1. GCC High Migration (MFS-0325-001): | [8 empty] | 60-90 days
2. Firewall Upgrade (MFS-0325-004): | [8 empty] | 90-120 days (includes procurement)
3. Intune Deployment (MFS-0325-002 003): | [8 empty] | 60-90 days (dependent on MFS-0325-001)
4. C3PAO Assessment (MFS-0325-013): | [8 empty] | 30-45 days (scheduling + assessment)
Total Critical Path Timeline: | [8 empty] | ~270 days (9 months) from start to CMMC certification
DEPENDENCIES MAPPING
MFS-0325-001 (GCC Migration): | Blocks → MFS-0325-002 003 010
MFS-0325-002 (Intune Deployment): | Blocks → MFS-0325-003 008 016
MFS-0325-004 (Firewall Upgrade): | Blocks → MFS-0325-014
All POA&Ms: | Block → MFS-0325-013 (C3PAO Assessment)
COMPLETION TRACKING
Status | Count | Percentage
Completed: | 0 | 0%
In Progress: | 3 | 17%
Not Started: | 14 | 78%
Ongoing: | 1 | 6%
Overdue Items (TBD dates): | Unknown - Scheduled completion dates not defined for most items